## Dashboard
AlKifah Contracting Company
Project Control Department
Cost Control Section
Project:
Issue Date:
Project Dashboard
Contracts Information
Contract Value |  |  | Duration (Days) |  | Planned Start Date
Initial Profit |  |  | Initial Profitability |  | Planned Finish Date
Revised Contract information
Change Order Value |  |  | Time Extension (Days) |  | Planned Start Date
Contract Value |  |  | Duration (Days) |  | Planned Finish Date
Budget Information
| Revision 0 |  |  | Last Revision
Total Budget Cost
Direct Cost
Indirect Cost
Management Reserve
EAC Contract Amount
Planned Profit
Planned Profitability
Actual Data